## Slide 1
00
PROGRAM BRIEFING · FOR STAKEHOLDERS
Lighthouse School System LMS
CSGLMS — what the program is building, how delivery is paced, and exactly where to look in Azure DevOps to see it for yourself.
CSG INFOTECH Private Limited
Org dev.azure.com/CSGInfotech
Prepared 31 Aug 2026

## Slide 2
01
THE PRODUCT
One platform, two clients, three pillars
CSGLMS is a multi-tenant school platform: a Next.js 15 web portal for six roles — Admin, Teacher, Student, Parent, Finance, HR — and a React Native (Expo SDK 52) native mobile app with offline sync, built as a composable modular monolith.
Web — Next.js 15
Admin · Teacher · Student · Parent · Finance · HR
Mobile — Expo SDK 52
React Native · offline-first via WatermelonDB
Core Foundation
Keycloak OIDC · Postgres row-level security · Cloudflare R2 · RabbitMQ · FCM push
Pillar 1 — LMS / SMS
M01–M20 · NestJS 10
Pillar 2 — AI RevOps
M21–M38 · FastAPI + LangGraph
Pillar 3 — AI Student Coach
M39–M50 · FastAPI + pgvector
Source: Welcome.md — Master Navigation Portal & architecture diagram.
02 / 13

## Slide 3
02
SCOPE
50 modules, three pillars, one schedule
50
Modules specified
171
API endpoints
497
Screens
122
Database tables
PILLAR | MODULES | COUNT | STACK
Pillar 1 — Core School Platform | M01–M20 | 20 | NestJS 10
Pillar 2 — AI Revenue Operations | M21–M38 | 18 | FastAPI + LangGraph
Pillar 3 — AI Student Coach | M39–M50 | 12 | FastAPI + pgvector
Scope figures as specified 14 Aug 2026 (Stakeholder Readiness Pack). Full spec detail: Repos → csglms-docs, 10 artifacts per module.
03 / 13

## Slide 4
03
SCHEDULE
134 working days, one protected buffer
Build window 2026-09-01 → 2027-02-07, Mon–Sat at 6 h/day — decided 2026-08-30 after two conflicting baselines were found live in the plan at once.
Sep 1
Phase 1 · Sep 1–Nov 13 · Core Platform (M01–M20)
Phase 2 · Nov 14–Dec 17 · AI RevOps (M21–M38)
Phase 3 · Dec 18–Feb 6 · AI Coach (M39–M50) + launch
Buffer · Feb 8–28 · reserved, not delivery capacity
134 net working days to 2027-02-07, then an 18-day risk buffer to 2027-02-28 — held for slippage, defect burn-down and re-test, never for planned scope.
Contractual baseline: 14 May 2027 (Employment Agreement CSG/EA/MU/011/26). External communication states this date only — the gap is deliberate protection.
Three contractual phases, each closed by a signed Phase Acceptance Certificate before the next begins.
Source: SCHEDULE-BASELINE.md & MILESTONE-ROADMAP-AND-DELIVERABLES.md. Rail is proportional to working days within the build + buffer window only; the May 2027 contractual date is not drawn to scale.
04 / 13

## Slide 5
04
MILESTONES
Nine milestones, each proven with a live demo
A milestone is not done because the code merged. It's done when the demo runs, end to end, in front of someone who didn't write it — live in the pilot school environment.
MILESTONE | WINDOW | SCOPE | GATE
MS-0 Core Foundation, Codegen & Design System | Sep 1–14 | Factory before product — auth, RLS, codegen, design tokens | Gate 1
MS-1 Academic Cluster | Sep 15–Oct 10 | M01, 02, 03, 04, 05, 06, 07, 12 | Gate 2
MS-2 Finance & HR Cluster | Oct 12–21 | M08, 09, 10, 11 | Gate 2
MS-3 Ops & Platform Cluster | Oct 22–Nov 13 | M13–M20 | Gate 2
MS-4 Lead Intake & Sales | Nov 14–30 | M21–M28 | Gate 2
MS-5 RevOps Analytics & Router | Dec 1–17 | M29–M38 | Gate 3
MS-6 AI Student Tutor & RAG | Dec 18–31 | M39–M44 | Gate 3
MS-7 Realtime Engine & Student Profile | Jan 1–13 | M45–M50 | Gate 3
MS-8 Hardening, UAT & Production Launch | Jan 14–Feb 6 | Full system, pen-test, load test, store launch | Gate 4
Source: MILESTONE-ROADMAP-AND-DELIVERABLES.md v3.0.0, generated from calendar.json.
05 / 13

## Slide 6
05
TEAM & CAPACITY
Five paid seats, one unpaid Tech Lead
SEAT | CAPACITY | COMMITTED | LOAD | FOCUS
Tech Lead / SDM / PM (25% hands-on — unpaid) | 201 h | 201 h | 100% | Architecture, review, gate evidence, stakeholders — allocated across all 134 working days, Sep 1 – Feb 6, every MS-0–MS-8 gate
Sr Fullstack | 804 h | 660 h | 63% | Web across all 50 modules; backend flex
Sr Backend AI | 804 h | 700 h | 66% | Schema, RLS, outbox, FastAPI/LangGraph
Jr Backend AI | 804 h | 520 h | 49% | NestJS controllers, OpenAPI contracts
Jr Frontend | 804 h | 702 h | 66% | React Native for 23 field-persona modules
UI/UX Designer (3-month engagement) | 468 h | 468 h | excl. | Design system, archetypes, component library
3,417 h
Core delivery capacity
2,728 h
Committed
79.8%
Utilisation · 689 h slack
Decided 2026-08-30 (SCHEDULE-BASELINE.md, calendar.json) — materially tighter than the 65.4% / 1,379 h figure some earlier client-facing documents carried. Tech Lead committed/load from TECH-LEAD-WORKBOOK.md's 134-row day-by-day schedule (all decided-baseline dates; TEAM-ASSIGNMENT-TABLE.md §6 milestone-ownership dates corrected 2026-08-31 to match).
06 / 13

## Slide 7
06
GOVERNANCE
Every phase ends with a signature, not a status update
ISO/IEC 12207 Gates 1–4 govern phase closure. Each of the three contractual phases closes with a signed Phase Acceptance Certificate.
CONTRACT PHASE | SCOPE | MILESTONES | WINDOW
Phase 1 | Core School Platform — M01–M20 | MS-0–MS-3 | Sep 1 – Nov 13
Phase 2 | AI Revenue Operations — M21–M38 | MS-4–MS-5 | Nov 14 – Dec 17
Phase 3 | AI Student Coach — M39–M50 + launch | MS-6–MS-8 | Dec 18 – Feb 6
The person who built a feature demonstrates it — they do not approve it. Contractual phase acceptance sits with the CEO, against the same evidence standard: showable, workable, functional. Working software demonstrated live — never documents alone.
Source: MILESTONE-ROADMAP-AND-DELIVERABLES.md §1; RISK-MANAGEMENT-REGISTER.md RSK-19.
07 / 13

## Slide 8
07
RISK
Four risks worth a stakeholder's attention
RSK-07 · Med / High
Codegen saving underdelivers.
~750 h of the plan assumes scaffolding saves ~15 h/module. Measured at the Gate 1 checkpoint inside MS-0 — 24 weeks left to react if it lands below ~10 h/module.
RSK-08 · High / High
Tech Lead overload.
One unpaid person holds SDM, PM, Tech Lead and CTO against a fixed date — recorded in the register itself as “the likeliest thing to sink the project.”
RSK-18 · Med / High
Contractual vs. internal date drift.
Two dates are in play. External communication states the 14 May 2027 contractual baseline only — quoting the internal target anywhere removes that protection.
RSK-20 · Low / High
Shared Azure DevOps process.
The Agile Tailored process is shared with another project; automation is verified to touch only work items and wiki, never process-level fields.
Full register — 20 tracked risks: 07-PMO-Financial-and-Executive-Tracking/RISK-MANAGEMENT-REGISTER.md (22 Aug 2026, v3.0.0).
08 / 13

## Slide 9
08
WHERE THE TRUTH LIVES
Azure DevOps is the single source of truth
Org: dev.azure.com/CSGInfotech. Everything on the previous slides is opinion until it's checked against one of these five areas.
Boards
Backlog, sprints, delivery plans — work item progress and burndown
Repos
csglms-docs — this wiki's source, 50 module spec packages
Wiki
CSG-LMS.wiki — this document set, navigable by section
Pipelines
azure-pipelines.yml — validates every generator with --check
Test Plans
Test case execution — licence-gated, see decisions requested
Every number in a stakeholder deck should be reproducible by opening a board — not by trusting the deck.
09 / 13

## Slide 10
09
HOW WORK IS TRACKED
Epic → Feature → Story → Task / Test Case
Epic
business goal
Feature
capability
User Story
shippable slice
Task — how it's built
Test Case — how it's verified
Status flow
1
New
2
Active
in development
3
Resolved
in pull request
4
Closed
verified in UAT
Every Task carries a parent Story; every Test Case links to the Story it verifies. That link, followed end to end, is what “traceability” means in practice — it's what to click through to check, not take on faith.
Source: 04-Operations-Runbooks-and-Skills/sops/Issues-and-ADO-Work-Item-Management-SOP.md
10 / 13

## Slide 11
10
A WALKTHROUGH
Five stops to see real status
1
Boards → Backlogs
Every Epic, Feature, Story, Task and Test Case, with parent links — the full inventory of declared work.
2
Boards → Sprints
The current two-week sprint, its board and burndown — what's committed versus what's actually moving.
3
Boards → Delivery Plans
One timeline across every team, milestones overlaid on sprints — the same roadmap as Slide 04, live.
4
Overview → Dashboards
Live widgets — velocity, burndown, work item counts — without digging through queries.
5
Overview → Wiki
CSG-LMS.wiki — this document set, including every source cited on this deck.
Ask to have it opened live in the meeting. Every figure in this briefing is meant to be checked, not taken on faith.
11 / 13

## Slide 12
11
CADENCE
Who's watching the board, and when
PROJECT MANAGER
Morning standup
08:30 – 09:00
• Yesterday's completions vs. schedule
• Blocker identification
• Backlog status on ADO Boards
SOFTWARE DELIVERY MANAGER
Mid-day pipeline review
12:00 – 12:30
• Active pull request queue on GitHub
• Automated test logs & coverage
• Branch & commit conventions
CHIEF TECHNOLOGY OFFICER
Evening deployment & log check
17:00 – 18:00
• Container resource utilisation
• Database backups to Cloudflare R2
• Approved PRs merged to staging
Bi-weekly: the PM submits a four-part steering-committee update — accomplishments, next deliverables, risks & escalations, capacity burn rate.
Source: PM-SDM-CTO-MASTER-MANAGEMENT-GUIDE.md §2; EXECUTIVE-STEERING-COMMITTEE-DASHBOARD.md §3.
12 / 13

## Slide 13
12
TODAY, AND WHAT'S ASKED OF YOU
Where things stand on 31 Aug 2026
The build opens tomorrow, 2026-09-01. The schedule baseline was decided 2026-08-30/31, so every date on this deck is current as of today.
# | DECISION REQUESTED | WHY IT'S ON THIS DECK
1 | Approve hiring for the 5 core seats + the 2-month designer engagement | Nothing on Slide 05's timeline starts without it
2 | Approve licence spend — 5 Basic seats, plus Basic + Test Plans if in-ADO test execution is required | Gates Test Plans access referenced on Slide 08
3 | Note the codegen assumption and the Gate 1 re-baseline checkpoint | RSK-07, Slide 07
4 | Nominate a DPO and confirm legal counsel | Longest lead time item; blocks Gate 4
Decisions list dated 14 Aug 2026 (Stakeholder Readiness Pack) — confirm status live in ADO before acting on it.
Contact Muhammad Usman Khan · SDM / Tech Lead
Org CSG INFOTECH Private Limited
ADO dev.azure.com/CSGInfotech
13 / 13